## Sheet1
Risk ID | Risk Title | Risk Description | Risk Category | Sub-Category | Sector | Department / Unit | Project Name | Project Code | Project Phase | Process Group | Risk Owner | Stakeholder Group | Date Identified | Probability Rating | Impact Rating | Risk Score | Qualitative Notes | Quantitative Notes | Mitigation Strategy | Contingency Plan | Status | Review Date | Monitoring Method | Control Method | Documentation Link | Lessons Learned | Source (Primary / Secondary) | Data Quality Flag | Primary RMS Step | RMS Step: Identification | RMS Step: Analysis – Qualitative | RMS Step: Analysis – Quantitative | RMS Step: Response Planning | RMS Step: Monitoring | RMS Step: Controlling | RMS Step: Documentation
R001 | Permit approval delay | Municipal permit takes longer than expected | Requirements | Regulatory | Network Infrastructure | SAQ Team | Metro Fiber Expansion | NFX-001 | Requirements | Initiating | SAQ Lead | Municipal Authority | Week 1 | High | High | 9 | Authority backlog noted |  | Follow up with authority | Adjust schedule | Open | Week 2 | Permit tracking | Regulatory enforcement | https://docs.example.com/permit-delay | Similar delay in 2023 | Primary | High | Risk Identification | ✓ |  |  |  |  | ✓
R002 | Landowner dispute | Landowner refuses site access | Requirements | Legal | Network Infrastructure | SAQ Team | Metro Fiber Expansion | NFX-001 | Requirements | Initiating | SAQ Lead | Landowner | Week 1 | High | High | 9 | Dispute raised during negotiation |  | Engage legal team | Identify alternate site | Open | Week 2 | Stakeholder meeting | Legal enforcement | https://docs.example.com/land-dispute | Case in 2021 | Primary | High | Risk Identification | ✓ |  |  |  |  | ✓
R003 | Environmental clearance rejection | Environmental permit denied due to protected zone | Requirements | Environmental | Network Infrastructure | SAQ Team | Metro Fiber Expansion | NFX-001 | Requirements | Planning | SAQ Lead | Environmental Authority | Week 2 | High | High | 9 | Protected area identified |  | Relocate site | Apply for exemption | Open | Week 3 | Permit tracking | Environmental compliance | https://docs.example.com/env-clearance | Similar in 2020 | Primary | High | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R004 | Utility conflict | Existing utilities obstruct planned route | Requirements | Regulatory | Network Infrastructure | SAQ Team | Metro Fiber Expansion | NFX-001 | Requirements | Planning | SAQ Lead | Utility Company | Week 3 | Medium | High | 6 | Conflict found in utility maps |  | Coordinate reroute | Negotiate relocation | Open | Week 4 | Utility mapping | Coordination control | https://docs.example.com/utility-conflict | Utility conflict in 2022 | Primary | Medium | Analysis – Qualitative |  | ✓ |  |  |  | ✓
R005 | Trench collapse risk | Unstable soil conditions in excavation area | Construction | Physical | Network Infrastructure | Civil Works Team | Metro Fiber Expansion | NFX-001 | Implementation | Executing | Civil Supervisor | Contractor | Week 5 | High | High | 9 | Geotechnical report shows instability |  | Shoring plan | Deploy trench boxes | Open | Week 6 | Site inspection | Safety enforcement | https://docs.example.com/trench-collapse | Incident in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R006 | Incorrect manhole base level | Manhole base set below design spec | Construction | Quality | Network Infrastructure | Civil Works Team | Metro Fiber Expansion | NFX-001 | Implementation | Executing | Civil Supervisor | Contractor | Week 6 | Medium | High | 6 | Inspection found level deviation |  | Reconstruct base | Adjust installation | Open | Week 7 | Level survey | Quality enforcement | https://docs.example.com/manhole-level | Deviation in 2020 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R007 | Poor duct compaction | Backfill not compacted to required density | Construction | Quality | Network Infrastructure | Civil Works Team | Metro Fiber Expansion | NFX-001 | Implementation | Executing | Civil Supervisor | Contractor | Week 6 | Medium | High | 6 | Compaction test failed |  | Recompact backfill | Retest density | Open | Week 7 | Compaction testing | Quality enforcement | https://docs.example.com/duct-compaction | Similar in 2022 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R008 | Flooding in excavation | Heavy rain floods open trenches | Construction | Environmental | Network Infrastructure | Civil Works Team | Metro Fiber Expansion | NFX-001 | Implementation | Executing | Civil Supervisor | Contractor | Week 7 | Medium | High | 6 | Weather forecast shows heavy rain |  | Install pumps | Cover trenches | Open | Week 8 | Site monitoring | Environmental control | https://docs.example.com/trench-flooding | Flood case in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R009 | Improper concrete curing | Concrete not cured to spec before load | Construction | Quality | Network Infrastructure | Civil Works Team | Metro Fiber Expansion | NFX-001 | Implementation | Executing | Civil Supervisor | Contractor | Week 7 | Medium | High | 6 | Curing time insufficient |  | Extend curing period | Retest strength | Open | Week 8 | Strength testing | Quality enforcement | https://docs.example.com/concrete-curing | Curing issue in 2020 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R010 | Improper grounding of racks | Grounding not compliant with electrical code | Electrical | Safety | Network Infrastructure | Electrical Works Team | Metro Fiber Expansion | NFX-001 | Implementation | Executing | Electrical Supervisor | Contractor | Week 8 | High | High | 9 | Inspection found missing ground |  | Install proper grounding | Retest compliance | Open | Week 9 | Electrical inspection | Safety enforcement | https://docs.example.com/grounding-error | Grounding issue in 2022 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R011 | Power cable insulation failure | Insulation damaged during installation | Electrical | Quality | Network Infrastructure | Electrical Works Team | Metro Fiber Expansion | NFX-001 | Implementation | Executing | Electrical Supervisor | Contractor | Week 8 | Medium | High | 6 | Visual inspection found damage |  | Replace cable | Retest insulation | Open | Week 9 | Cable testing | Quality enforcement | https://docs.example.com/cable-insulation | Failure in 2021 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R012 | Delay in electrical panel installation | Panels delivered late to site | Electrical | Logistics | Network Infrastructure | Electrical Works Team | Metro Fiber Expansion | NFX-001 | Implementation | Executing | Electrical Supervisor | Vendor | Week 8 | Medium | Medium | 4 | Vendor shipment delayed |  | Reschedule installation | Use backup panels | Open | Week 9 | Delivery tracking | Logistics control | https://docs.example.com/panel-delay | Delay in 2020 | Primary | Medium | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R013 | Fiber splice loss above limit | High dB loss at splice points | Technical | Fiber | Network Infrastructure | Telecom Implementation Team | Metro Fiber Expansion | NFX-001 | Implementation | Executing | Telecom Supervisor | Contractor | Week 9 | Medium | High | 6 | OTDR test shows high loss | Optical budget calc | Re-splice fibers | Replace connectors | Open | Week 10 | Optical testing | Performance tuning | https://docs.example.com/splice-loss | Similar in 2022 | Primary | High | Analysis – Quantitative |  | ✓ | ✓ |  |  | ✓
R014 | GSM antenna misalignment | Antenna not aligned to design azimuth | Technical | GSM | Network Infrastructure | Telecom Implementation Team | Metro Fiber Expansion | NFX-001 | Implementation | Executing | Telecom Supervisor | Contractor | Week 9 | Medium | High | 6 | Alignment check failed |  | Realign antenna | Retest coverage | Open | Week 10 | Signal testing | Quality enforcement | https://docs.example.com/antenna-misalignment | Misalignment in 2021 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R015 | Integration software bug | Software error during site integration | Technical | Integration | Network Infrastructure | Telecom Implementation Team | Metro Fiber Expansion | NFX-001 | Implementation | Executing | Telecom Supervisor | Vendor | Week 10 | Medium | High | 6 | Bug found in integration test |  | Apply patch | Retest integration | Open | Week 11 | Integration logs | Quality control | https://docs.example.com/integration-bug | Bug in 2020 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R016 | Failed acceptance test | Acceptance criteria not met during QA | Quality | Testing | Network Infrastructure | QA Team | Metro Fiber Expansion | NFX-001 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | High | High | 9 | Test results below threshold |  | Identify root cause | Retest after fix | Open | Week 12 | Test logs | Quality enforcement | https://docs.example.com/acceptance-fail | Fail in 2022 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R017 | Missing as-built drawings | Final as-built documentation not prepared before acceptance | Quality | Documentation | Network Infrastructure | QA Team | Metro Fiber Expansion | NFX-001 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | Medium | High | 6 | No updated drawings in repository |  | Prepare as-built set | Submit for approval | Open | Week 12 | Doc review | Documentation control | https://docs.example.com/missing-asbuilt | Similar gap in 2020 | Primary | High | Documentation | [5 empty] | ✓
R018 | Acceptance criteria misinterpretation | Stakeholders apply incorrect acceptance standards | Quality | Compliance | Network Infrastructure | QA Team | Metro Fiber Expansion | NFX-001 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | Medium | High | 6 | Standards mismatch noted |  | Clarify acceptance checklist | Align with contract | Open | Week 12 | Acceptance review | Compliance enforcement | https://docs.example.com/criteria-error | Case in 2021 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R019 | Preventive maintenance schedule gap | Maintenance plan missing critical inspections | Maintenance | Planning | Network Infrastructure | Operations Team | Metro Fiber Expansion | NFX-001 | Maintenance | Closing | Maintenance Lead | Stakeholders | Week 13 | Medium | Medium | 4 | Missing inspection tasks |  | Revise schedule | Train maintenance staff | Open | Week 14 | Plan review | Compliance check | https://docs.example.com/maintenance-gap | Gap in 2022 | Primary | Medium | Documentation | [5 empty] | ✓
R020 | Security breach risk | Unauthorized access to site during maintenance | Maintenance | Security | Network Infrastructure | Operations Team | Metro Fiber Expansion | NFX-001 | Maintenance | Closing | Maintenance Lead | Security Contractor | Week 13 | High | High | 9 | Access control failure |  | Upgrade locks | Implement ID checks | Open | Week 14 | Security audit | Security enforcement | https://docs.example.com/security-breach | Breach in 2023 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R021 | Permit scope mismatch | Permit terms unclear, leading to potential scope overrun | Requirements | Regulatory | Network Infrastructure | SAQ Team | Regional Backbone Upgrade | RBU-002 | Requirements | Initiating | SAQ Lead | Municipal Authority | Week 1 | High | High | 9 | Permit wording ambiguous |  | Clarify with authority | Adjust work plan | Open | Week 2 | Permit tracking | Regulatory enforcement | https://docs.example.com/permit-scope | Similar in 2022 | Primary | High | Risk Identification | ✓ |  |  |  |  | ✓
R022 | Land survey error | Survey data inaccurate, affecting site boundaries | Requirements | Technical | Network Infrastructure | SAQ Team | Regional Backbone Upgrade | RBU-002 | Requirements | Planning | SAQ Lead | Survey Contractor | Week 2 | Medium | High | 6 | Boundary mismatch found |  | Resurvey site | Update maps | Open | Week 3 | Survey review | Quality control | https://docs.example.com/survey-error | Error in 2020 | Primary | Medium | Analysis – Qualitative |  | ✓ |  |  |  | ✓
R023 | Community opposition | Local residents object to site construction | Requirements | Stakeholder | Network Infrastructure | SAQ Team | Regional Backbone Upgrade | RBU-002 | Requirements | Planning | SAQ Lead | Community Group | Week 3 | Medium | High | 6 | Objection raised in meeting |  | Engage community | Offer mitigation plan | Open | Week 4 | Stakeholder engagement | Conflict resolution | https://docs.example.com/community-opposition | Similar in 2021 | Primary | High | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R024 | Trench collapse risk | Loose soil in excavation area | Construction | Physical | Network Infrastructure | Civil Works Team | Regional Backbone Upgrade | RBU-002 | Implementation | Executing | Civil Supervisor | Contractor | Week 5 | High | High | 9 | Geotechnical report shows instability |  | Shoring plan | Deploy trench boxes | Open | Week 6 | Site inspection | Safety enforcement | https://docs.example.com/trench-collapse | Incident in 2023 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R025 | Incorrect duct alignment | Ducts laid outside design path | Construction | Quality | Network Infrastructure | Civil Works Team | Regional Backbone Upgrade | RBU-002 | Implementation | Executing | Civil Supervisor | Contractor | Week 6 | Medium | High | 6 | Inspection found deviation |  | Relocate ducts | Adjust installation | Open | Week 7 | Route inspection | Quality enforcement | https://docs.example.com/duct-alignment | Deviation in 2021 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R026 | Poor compaction | Backfill density below spec | Construction | Quality | Network Infrastructure | Civil Works Team | Regional Backbone Upgrade | RBU-002 | Implementation | Executing | Civil Supervisor | Contractor | Week 6 | Medium | High | 6 | Compaction test failed |  | Recompact backfill | Retest density | Open | Week 7 | Compaction testing | Quality enforcement | https://docs.example.com/compaction-error | Similar in 2020 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R027 | Flooding in trench | Heavy rain floods excavation | Construction | Environmental | Network Infrastructure | Civil Works Team | Regional Backbone Upgrade | RBU-002 | Implementation | Executing | Civil Supervisor | Contractor | Week 7 | Medium | High | 6 | Weather forecast shows heavy rain |  | Install pumps | Cover trenches | Open | Week 8 | Site monitoring | Environmental control | https://docs.example.com/trench-flooding | Flood case in 2022 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R028 | Improper concrete curing | Concrete not cured to spec before load | Construction | Quality | Network Infrastructure | Civil Works Team | Regional Backbone Upgrade | RBU-002 | Implementation | Executing | Civil Supervisor | Contractor | Week 7 | Medium | High | 6 | Curing time insufficient |  | Extend curing period | Retest strength | Open | Week 8 | Strength testing | Quality enforcement | https://docs.example.com/concrete-curing | Curing issue in 2021 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R029 | Improper grounding of racks | Grounding not compliant with electrical code | Electrical | Safety | Network Infrastructure | Electrical Works Team | Regional Backbone Upgrade | RBU-002 | Implementation | Executing | Electrical Supervisor | Contractor | Week 8 | High | High | 9 | Inspection found missing ground |  | Install proper grounding | Retest compliance | Open | Week 9 | Electrical inspection | Safety enforcement | https://docs.example.com/grounding-error | Grounding issue in 2020 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R030 | Power cable insulation failure | Insulation damaged during installation | Electrical | Quality | Network Infrastructure | Electrical Works Team | Regional Backbone Upgrade | RBU-002 | Implementation | Executing | Electrical Supervisor | Contractor | Week 8 | Medium | High | 6 | Visual inspection found damage |  | Replace cable | Retest insulation | Open | Week 9 | Cable testing | Quality enforcement | https://docs.example.com/cable-insulation | Failure in 2022 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R031 | Delay in electrical panel installation | Panels delivered late to site | Electrical | Logistics | Network Infrastructure | Electrical Works Team | Regional Backbone Upgrade | RBU-002 | Implementation | Executing | Electrical Supervisor | Vendor | Week 8 | Medium | Medium | 4 | Vendor shipment delayed |  | Reschedule installation | Use backup panels | Open | Week 9 | Delivery tracking | Logistics control | https://docs.example.com/panel-delay | Delay in 2021 | Primary | Medium | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R032 | Fiber splice loss above limit | High dB loss at splice points | Technical | Fiber | Network Infrastructure | Telecom Implementation Team | Regional Backbone Upgrade | RBU-002 | Implementation | Executing | Telecom Supervisor | Contractor | Week 9 | Medium | High | 6 | OTDR test shows high loss | Optical budget calc | Re-splice fibers | Replace connectors | Open | Week 10 | Optical testing | Performance tuning | https://docs.example.com/splice-loss | Similar in 2020 | Primary | High | Analysis – Quantitative |  | ✓ | ✓ |  |  | ✓
R033 | GSM antenna misalignment | Antenna not aligned to design azimuth | Technical | GSM | Network Infrastructure | Telecom Implementation Team | Regional Backbone Upgrade | RBU-002 | Implementation | Executing | Telecom Supervisor | Contractor | Week 9 | Medium | High | 6 | Alignment check failed |  | Realign antenna | Retest coverage | Open | Week 10 | Signal testing | Quality enforcement | https://docs.example.com/antenna-misalignment | Misalignment in 2023 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R034 | Integration software bug | Software error during site integration | Technical | Integration | Network Infrastructure | Telecom Implementation Team | Regional Backbone Upgrade | RBU-002 | Implementation | Executing | Telecom Supervisor | Vendor | Week 10 | Medium | High | 6 | Bug found in integration test |  | Apply patch | Retest integration | Open | Week 11 | Integration logs | Quality control | https://docs.example.com/integration-bug | Bug in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R035 | Failed acceptance test | Acceptance criteria not met during QA | Quality | Testing | Network Infrastructure | QA Team | Regional Backbone Upgrade | RBU-002 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | High | High | 9 | Test results below threshold |  | Identify root cause | Retest after fix | Open | Week 12 | Test logs | Quality enforcement | https://docs.example.com/acceptance-fail | Fail in 2020 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R036 | Missing as-built drawings | Final as-built documentation not prepared before acceptance | Quality | Documentation | Network Infrastructure | QA Team | Regional Backbone Upgrade | RBU-002 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | Medium | High | 6 | No updated drawings in repository |  | Prepare as-built set | Submit for approval | Open | Week 12 | Doc review | Documentation control | https://docs.example.com/missing-asbuilt | Similar gap in 2022 | Primary | High | Documentation | [5 empty] | ✓
R037 | Acceptance criteria misinterpretation | Stakeholders apply incorrect acceptance standards | Quality | Compliance | Network Infrastructure | QA Team | Regional Backbone Upgrade | RBU-002 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | Medium | High | 6 | Standards mismatch noted |  | Clarify acceptance checklist | Align with contract | Open | Week 12 | Acceptance review | Compliance enforcement | https://docs.example.com/criteria-error | Case in 2021 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R038 | Preventive maintenance schedule gap | Maintenance plan missing critical inspections | Maintenance | Planning | Network Infrastructure | Operations Team | Regional Backbone Upgrade | RBU-002 | Maintenance | Closing | Maintenance Lead | Stakeholders | Week 13 | Medium | Medium | 4 | Missing inspection tasks |  | Revise schedule | Train maintenance staff | Open | Week 14 | Plan review | Compliance check | https://docs.example.com/maintenance-gap | Gap in 2020 | Primary | Medium | Documentation | [5 empty] | ✓
R039 | Security breach risk | Unauthorized access to site during maintenance | Maintenance | Security | Network Infrastructure | Operations Team | Regional Backbone Upgrade | RBU-002 | Maintenance | Closing | Maintenance Lead | Security Contractor | Week 13 | High | High | 9 | Access control failure |  | Upgrade locks | Implement ID checks | Open | Week 14 | Security audit | Security enforcement | https://docs.example.com/security-breach | Breach in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R040 | Spare parts shortage | Insufficient spare parts for maintenance tasks | Maintenance | Logistics | Network Infrastructure | Operations Team | Regional Backbone Upgrade | RBU-002 | Maintenance | Closing | Maintenance Lead | Vendor | Week 13 | Medium | High | 6 | Inventory below threshold |  | Reorder parts | Use alternate supplier | Open | Week 14 | Inventory tracking | Logistics control | https://docs.example.com/spare-parts-shortage | Shortage in 2023 | Primary | High | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R041 | Permit approval delay | Municipal permit takes longer than expected | Requirements | Regulatory | Network Infrastructure | SAQ Team | Municipal Ring Deployment | MRD-003 | Requirements | Initiating | SAQ Lead | Municipal Authority | Week 1 | High | High | 9 | Authority backlog noted |  | Follow up with authority | Adjust schedule | Open | Week 2 | Permit tracking | Regulatory enforcement | https://docs.example.com/permit-delay | Similar delay in 2022 | Primary | High | Risk Identification | ✓ |  |  |  |  | ✓
R042 | Landowner dispute | Landowner refuses rooftop site access | Requirements | Legal | Network Infrastructure | SAQ Team | Municipal Ring Deployment | MRD-003 | Requirements | Initiating | SAQ Lead | Landowner | Week 1 | High | High | 9 | Dispute raised during negotiation |  | Engage legal team | Identify alternate site | Open | Week 2 | Stakeholder meeting | Legal enforcement | https://docs.example.com/land-dispute | Case in 2021 | Primary | High | Risk Identification | ✓ |  |  |  |  | ✓
R043 | Structural load exceedance | Rooftop site exceeds allowable load for non‑penetrating pole | Construction | Physical | Network Infrastructure | Civil Works Team | Municipal Ring Deployment | MRD-003 | Implementation | Executing | Civil Supervisor | Structural Engineer | Week 5 | High | High | 9 | Load calc shows exceedance |  | Reinforce structure | Reduce equipment weight | Open | Week 6 | Load testing | Structural compliance | https://docs.example.com/load-exceedance | Similar in 2020 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R044 | Foundation depth error | Monopole foundation depth below design spec | Construction | Quality | Network Infrastructure | Civil Works Team | Municipal Ring Deployment | MRD-003 | Implementation | Executing | Civil Supervisor | Contractor | Week 5 | Medium | High | 6 | Inspection found shallow depth |  | Excavate deeper | Recast foundation | Open | Week 6 | Foundation survey | Quality enforcement | https://docs.example.com/foundation-error | Error in 2023 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R045 | Anchor bolt misalignment | Anchor bolts for self‑supporting tower misaligned | Construction | Quality | Network Infrastructure | Civil Works Team | Municipal Ring Deployment | MRD-003 | Implementation | Executing | Civil Supervisor | Contractor | Week 6 | Medium | High | 6 | Template shift during casting |  | Realign bolts | Retest alignment | Open | Week 7 | Alignment check | Quality enforcement | https://docs.example.com/bolt-misalignment | Similar in 2021 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R046 | Improper sealing around mounts | Water leakage risk at rooftop wall mount | Construction | Environmental | Network Infrastructure | Civil Works Team | Municipal Ring Deployment | MRD-003 | Implementation | Executing | Civil Supervisor | Contractor | Week 7 | Medium | High | 6 | Sealant gaps found |  | Apply proper sealant | Retest for leaks | Open | Week 8 | Leak testing | Environmental control | https://docs.example.com/mount-sealing | Leak case in 2020 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R047 | Improper grounding of racks | Grounding not compliant with electrical code | Electrical | Safety | Network Infrastructure | Electrical Works Team | Municipal Ring Deployment | MRD-003 | Implementation | Executing | Electrical Supervisor | Contractor | Week 8 | High | High | 9 | Inspection found missing ground |  | Install proper grounding | Retest compliance | Open | Week 9 | Electrical inspection | Safety enforcement | https://docs.example.com/grounding-error | Grounding issue in 2022 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R048 | Power cable insulation failure | Insulation damaged during installation | Electrical | Quality | Network Infrastructure | Electrical Works Team | Municipal Ring Deployment | MRD-003 | Implementation | Executing | Electrical Supervisor | Contractor | Week 8 | Medium | High | 6 | Visual inspection found damage |  | Replace cable | Retest insulation | Open | Week 9 | Cable testing | Quality enforcement | https://docs.example.com/cable-insulation | Failure in 2021 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R049 | Delay in electrical panel installation | Panels delivered late to site | Electrical | Logistics | Network Infrastructure | Electrical Works Team | Municipal Ring Deployment | MRD-003 | Implementation | Executing | Electrical Supervisor | Vendor | Week 8 | Medium | Medium | 4 | Vendor shipment delayed |  | Reschedule installation | Use backup panels | Open | Week 9 | Delivery tracking | Logistics control | https://docs.example.com/panel-delay | Delay in 2020 | Primary | Medium | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R050 | Fiber splice loss above limit | High dB loss at splice points | Technical | Fiber | Network Infrastructure | Telecom Implementation Team | Municipal Ring Deployment | MRD-003 | Implementation | Executing | Telecom Supervisor | Contractor | Week 9 | Medium | High | 6 | OTDR test shows high loss | Optical budget calc | Re-splice fibers | Replace connectors | Open | Week 10 | Optical testing | Performance tuning | https://docs.example.com/splice-loss | Similar in 2022 | Primary | High | Analysis – Quantitative |  | ✓ | ✓ |  |  | ✓
R051 | GSM antenna misalignment | Antenna not aligned to design azimuth | Technical | GSM | Network Infrastructure | Telecom Implementation Team | Municipal Ring Deployment | MRD-003 | Implementation | Executing | Telecom Supervisor | Contractor | Week 9 | Medium | High | 6 | Alignment check failed |  | Realign antenna | Retest coverage | Open | Week 10 | Signal testing | Quality enforcement | https://docs.example.com/antenna-misalignment | Misalignment in 2021 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R052 | Integration software bug | Software error during site integration | Technical | Integration | Network Infrastructure | Telecom Implementation Team | Municipal Ring Deployment | MRD-003 | Implementation | Executing | Telecom Supervisor | Vendor | Week 10 | Medium | High | 6 | Bug found in integration test |  | Apply patch | Retest integration | Open | Week 11 | Integration logs | Quality control | https://docs.example.com/integration-bug | Bug in 2020 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R053 | Failed acceptance test | Acceptance criteria not met during QA | Quality | Testing | Network Infrastructure | QA Team | Municipal Ring Deployment | MRD-003 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | High | High | 9 | Test results below threshold |  | Identify root cause | Retest after fix | Open | Week 12 | Test logs | Quality enforcement | https://docs.example.com/acceptance-fail | Fail in 2023 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R054 | Missing as-built drawings | Final as-built documentation not prepared before acceptance | Quality | Documentation | Network Infrastructure | QA Team | Municipal Ring Deployment | MRD-003 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | Medium | High | 6 | No updated drawings in repository |  | Prepare as-built set | Submit for approval | Open | Week 12 | Doc review | Documentation control | https://docs.example.com/missing-asbuilt | Similar gap in 2021 | Primary | High | Documentation | [5 empty] | ✓
R055 | Acceptance criteria misinterpretation | Stakeholders apply incorrect acceptance standards | Quality | Compliance | Network Infrastructure | QA Team | Municipal Ring Deployment | MRD-003 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | Medium | High | 6 | Standards mismatch noted |  | Clarify acceptance checklist | Align with contract | Open | Week 12 | Acceptance review | Compliance enforcement | https://docs.example.com/criteria-error | Case in 2020 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R056 | Preventive maintenance schedule gap | Maintenance plan missing critical inspections | Maintenance | Planning | Network Infrastructure | Operations Team | Municipal Ring Deployment | MRD-003 | Maintenance | Closing | Maintenance Lead | Stakeholders | Week 13 | Medium | Medium | 4 | Missing inspection tasks |  | Revise schedule | Train maintenance staff | Open | Week 14 | Plan review | Compliance check | https://docs.example.com/maintenance-gap | Gap in 2022 | Primary | Medium | Documentation | [5 empty] | ✓
R057 | Security breach risk | Unauthorized access to site during maintenance | Maintenance | Security | Network Infrastructure | Operations Team | Municipal Ring Deployment | MRD-003 | Maintenance | Closing | Maintenance Lead | Security Contractor | Week 13 | High | High | 9 | Access control failure |  | Upgrade locks | Implement ID checks | Open | Week 14 | Security audit | Security enforcement | https
R058 | Spare parts shortage | Insufficient spare parts for maintenance tasks | Maintenance | Logistics | Network Infrastructure | Operations Team | Municipal Ring Deployment | MRD-003 | Maintenance | Closing | Maintenance Lead | Vendor | Week 13 | Medium | High | 6 | Inventory below threshold |  | Reorder parts | Use alternate supplier | Open | Week 14 | Inventory tracking | Logistics control | https://docs.example.com/spare-parts-shortage | Shortage in 2021 | Primary | High | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R059 | Preventive maintenance training gap | Maintenance staff not trained on new equipment | Maintenance | Training | Network Infrastructure | Operations Team | Municipal Ring Deployment | MRD-003 | Maintenance | Closing | Maintenance Lead | Stakeholders | Week 13 | Medium | Medium | 4 | Training records incomplete |  | Conduct refresher training | Update manuals | Open | Week 14 | Training review | Compliance check | https://docs.example.com/training-gap | Gap in 2020 | Primary | Medium | Documentation | [5 empty] | ✓
R060 | Obsolete firmware risk | Equipment firmware outdated, causing performance issues | Maintenance | Technical | Network Infrastructure | Operations Team | Municipal Ring Deployment | MRD-003 | Maintenance | Closing | Maintenance Lead | Vendor | Week 13 | Medium | High | 6 | Firmware version unsupported |  | Update firmware | Test performance | Open | Week 14 | Firmware audit | Quality control | https://docs.example.com/firmware-risk | Similar in 2023 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R061 | Permit processing delay | Authority backlog slows rooftop site approval | Requirements | Regulatory | Network Infrastructure | SAQ Team | Industrial Zone Connectivity | IZC-004 | Requirements | Initiating | SAQ Lead | Municipal Authority | Week 1 | High | High | 9 | Permit queue extended |  | Follow up with authority | Adjust schedule | Open | Week 2 | Permit tracking | Regulatory enforcement | https://docs.example.com/permit-delay | Similar delay in 2021 | Primary | High | Risk Identification | ✓ |  |  |  |  | ✓
R062 | Boundary survey discrepancy | Survey data conflicts with municipal records | Requirements | Technical | Network Infrastructure | SAQ Team | Industrial Zone Connectivity | IZC-004 | Requirements | Planning | SAQ Lead | Survey Contractor | Week 2 | Medium | High | 6 | Boundary mismatch found |  | Resurvey site | Update maps | Open | Week 3 | Survey review | Quality control | https://docs.example.com/survey-error | Error in 2020 | Primary | Medium | Analysis – Qualitative |  | ✓ |  |  |  | ✓
R063 | Community protest | Residents object to Greenfield tower construction | Requirements | Stakeholder | Network Infrastructure | SAQ Team | Industrial Zone Connectivity | IZC-004 | Requirements | Planning | SAQ Lead | Community Group | Week 3 | Medium | High | 6 | Objection raised in meeting |  | Engage community | Offer mitigation plan | Open | Week 4 | Stakeholder engagement | Conflict resolution | https://docs.example.com/community-opposition | Similar in 2022 | Primary | High | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R064 | Foundation settlement risk | Soil compaction inadequate for monopole base | Construction | Physical | Network Infrastructure | Civil Works Team | Industrial Zone Connectivity | IZC-004 | Implementation | Executing | Civil Supervisor | Geotechnical Engineer | Week 5 | High | High | 9 | Settlement observed in test pit |  | Recompact soil | Reinforce foundation | Open | Week 6 | Foundation survey | Structural compliance | https://docs.example.com/foundation-settlement | Similar in 2020 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R065 | Incorrect tower plumb | Tower tilt exceeds tolerance during erection | Construction | Quality | Network Infrastructure | Civil Works Team | Industrial Zone Connectivity | IZC-004 | Implementation | Executing | Civil Supervisor | Contractor | Week 6 | Medium | High | 6 | Plumb check failed |  | Realign tower | Retest alignment | Open | Week 7 | Alignment check | Quality enforcement | https://docs.example.com/tower-plumb-error | Error in 2023 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R066 | Rooftop wind uplift risk | Non‑penetrating pole at risk in high winds | Construction | Safety | Network Infrastructure | Civil Works Team | Industrial Zone Connectivity | IZC-004 | Implementation | Executing | Civil Supervisor | Structural Engineer | Week 6 | Medium | High | 6 | Wind load calc exceeded |  | Add ballast | Install tie‑downs | Open | Week 7 | Wind testing | Safety enforcement | https://docs.example.com/wind-uplift | Similar in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R067 | Improper grounding of racks | Grounding not compliant with electrical code | Electrical | Safety | Network Infrastructure | Electrical Works Team | Industrial Zone Connectivity | IZC-004 | Implementation | Executing | Electrical Supervisor | Contractor | Week 8 | High | High | 9 | Inspection found missing ground |  | Install proper grounding | Retest compliance | Open | Week 9 | Electrical inspection | Safety enforcement | https://docs.example.com/grounding-error | Grounding issue in 2020 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R068 | Power cable insulation failure | Insulation damaged during installation | Electrical | Quality | Network Infrastructure | Electrical Works Team | Industrial Zone Connectivity | IZC-004 | Implementation | Executing | Electrical Supervisor | Contractor | Week 8 | Medium | High | 6 | Visual inspection found damage |  | Replace cable | Retest insulation | Open | Week 9 | Cable testing | Quality enforcement | https://docs.example.com/cable-insulation | Failure in 2022 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R069 | Delay in electrical panel installation | Panels delivered late to site | Electrical | Logistics | Network Infrastructure | Electrical Works Team | Industrial Zone Connectivity | IZC-004 | Implementation | Executing | Electrical Supervisor | Vendor | Week 8 | Medium | Medium | 4 | Vendor shipment delayed |  | Reschedule installation | Use backup panels | Open | Week 9 | Delivery tracking | Logistics control | https://docs.example.com/panel-delay | Delay in 2021 | Primary | Medium | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R070 | Fiber splice loss above limit | High dB loss at splice points | Technical | Fiber | Network Infrastructure | Telecom Implementation Team | Industrial Zone Connectivity | IZC-004 | Implementation | Executing | Telecom Supervisor | Contractor | Week 9 | Medium | High | 6 | OTDR test shows high loss | Optical budget calc | Re-splice fibers | Replace connectors | Open | Week 10 | Optical testing | Performance tuning | https://docs.example.com/splice-loss | Similar in 2020 | Primary | High | Analysis – Quantitative |  | ✓ | ✓ |  |  | ✓
R071 | GSM antenna misalignment | Antenna not aligned to design azimuth | Technical | GSM | Network Infrastructure | Telecom Implementation Team | Industrial Zone Connectivity | IZC-004 | Implementation | Executing | Telecom Supervisor | Contractor | Week 9 | Medium | High | 6 | Alignment check failed |  | Realign antenna | Retest coverage | Open | Week 10 | Signal testing | Quality enforcement | https://docs.example.com/antenna-misalignment | Misalignment in 2023 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R072 | Integration software bug | Software error during site integration | Technical | Integration | Network Infrastructure | Telecom Implementation Team | Industrial Zone Connectivity | IZC-004 | Implementation | Executing | Telecom Supervisor | Vendor | Week 10 | Medium | High | 6 | Bug found in integration test |  | Apply patch | Retest integration | Open | Week 11 | Integration logs | Quality control | https://docs.example.com/integration-bug | Bug in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R073 | Failed acceptance test | Acceptance criteria not met during QA | Quality | Testing | Network Infrastructure | QA Team | Industrial Zone Connectivity | IZC-004 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | High | High | 9 | Test results below threshold |  | Identify root cause | Retest after fix | Open | Week 12 | Test logs | Quality enforcement | https://docs.example.com/acceptance-fail | Fail in 2020 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R074 | Missing as-built drawings | Final as-built documentation not prepared before acceptance | Quality | Documentation | Network Infrastructure | QA Team | Industrial Zone Connectivity | IZC-004 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | Medium | High | 6 | No updated drawings in repository |  | Prepare as-built set | Submit for approval | Open | Week 12 | Doc review | Documentation control | https://docs.example.com/missing-asbuilt | Similar gap in 2022 | Primary | High | Documentation | [5 empty] | ✓
R075 | Acceptance criteria misinterpretation | Stakeholders apply incorrect acceptance standards | Quality | Compliance | Network Infrastructure | QA Team | Industrial Zone Connectivity | IZC-004 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | Medium | High | 6 | Standards mismatch noted |  | Clarify acceptance checklist | Align with contract | Open | Week 12 | Acceptance review | Compliance enforcement | https://docs.example.com/criteria-error | Case in 2021 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R076 | Preventive maintenance schedule gap | Maintenance plan missing critical inspections | Maintenance | Planning | Network Infrastructure | Operations Team | Industrial Zone Connectivity | IZC-004 | Maintenance | Closing | Maintenance Lead | Stakeholders | Week 13 | Medium | Medium | 4 | Missing inspection tasks |  | Revise schedule | Train maintenance staff | Open | Week 14 | Plan review | Compliance check | https://docs.example.com/maintenance-gap | Gap in 2020 | Primary | Medium | Documentation | [5 empty] | ✓
R077 | Security breach risk | Unauthorized access to site during maintenance | Maintenance | Security | Network Infrastructure | Operations Team | Industrial Zone Connectivity | IZC-004 | Maintenance | Closing | Maintenance Lead | Security Contractor | Week 13 | High | High | 9 | Access control failure |  | Upgrade locks | Implement ID checks | Open | Week 14 | Security audit | Security enforcement | https://docs.example.com/security-breach | Breach in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R078 | Spare parts shortage | Insufficient spare parts for maintenance tasks | Maintenance | Logistics | Network Infrastructure | Operations Team | Industrial Zone Connectivity | IZC-004 | Maintenance | Closing | Maintenance Lead | Vendor | Week 13 | Medium | High | 6 | Inventory below threshold |  | Reorder parts | Use alternate supplier | Open | Week 14 | Inventory tracking | Logistics control | https://docs.example.com/spare-parts-shortage | Shortage in 2023 | Primary | High | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R079 | Preventive maintenance training gap | Maintenance staff not trained on new equipment | Maintenance | Training | Network Infrastructure | Operations Team | Industrial Zone Connectivity | IZC-004 | Maintenance | Closing | Maintenance Lead | Stakeholders | Week 13 | Medium | Medium | 4 | Training records incomplete |  | Conduct refresher training | Update manuals | Open | Week 14 | Training review | Compliance check | https://docs.example.com/training-gap | Gap in 2021 | Primary | Medium | Documentation | [5 empty] | ✓
R080 | Obsolete firmware risk | Equipment firmware outdated, causing performance issues | Maintenance | Technical | Network Infrastructure | Operations Team | Industrial Zone Connectivity | IZC-004 | Maintenance | Closing | Maintenance Lead | Vendor | Week 13 | Medium | High | 6 | Firmware version unsupported |  | Update firmware | Test performance | Open | Week 14 | Firmware audit | Quality control | https://docs.example.com/firmware-risk | Similar in 2020 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R081 | Permit approval delay | Municipal permit takes longer than expected | Requirements | Regulatory | Network Infrastructure | SAQ Team | Data Center Link Integration | DCLI-005 | Requirements | Initiating | SAQ Lead | Municipal Authority | Week 1 | High | High | 9 | Authority backlog noted |  | Follow up with authority | Adjust schedule | Open | Week 2 | Permit tracking | Regulatory enforcement | https://docs.example.com/permit-delay | Similar delay in 2022 | Primary | High | Risk Identification | ✓ |  |  |  |  | ✓
R082 | Landowner dispute | Landowner refuses rooftop site access | Requirements | Legal | Network Infrastructure | SAQ Team | Data Center Link Integration | DCLI-005 | Requirements | Initiating | SAQ Lead | Landowner | Week 1 | High | High | 9 | Dispute raised during negotiation |  | Engage legal team | Identify alternate site | Open | Week 2 | Stakeholder meeting | Legal enforcement | https://docs.example.com/land-dispute | Case in 2021 | Primary | High | Risk Identification | ✓ |  |  |  |  | ✓
R083 | Environmental clearance rejection | Environmental permit denied due to protected zone | Requirements | Environmental | Network Infrastructure | SAQ Team | Data Center Link Integration | DCLI-005 | Requirements | Planning | SAQ Lead | Environmental Authority | Week 2 | High | High | 9 | Protected area identified |  | Relocate site | Apply for exemption | Open | Week 3 | Permit tracking | Environmental compliance | https://docs.example.com/env-clearance | Similar in 2020 | Primary | High | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R084 | Foundation depth error | Monopole foundation depth below design spec | Construction | Quality | Network Infrastructure | Civil Works Team | Data Center Link Integration | DCLI-005 | Implementation | Executing | Civil Supervisor | Contractor | Week 5 | Medium | High | 6 | Inspection found shallow depth |  | Excavate deeper | Recast foundation | Open | Week 6 | Foundation survey | Quality enforcement | https://docs.example.com/foundation-error | Error in 2023 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R085 | Anchor bolt misalignment | Anchor bolts for self‑supporting tower misaligned | Construction | Quality | Network Infrastructure | Civil Works Team | Data Center Link Integration | DCLI-005 | Implementation | Executing | Civil Supervisor | Contractor | Week 6 | Medium | High | 6 | Template shift during casting |  | Realign bolts | Retest alignment | Open | Week 7 | Alignment check | Quality enforcement | https://docs.example.com/bolt-misalignment | Similar in 2021 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R086 | Rooftop wind uplift risk | Non‑penetrating pole at risk in high winds | Construction | Safety | Network Infrastructure | Civil Works Team | Data Center Link Integration | DCLI-005 | Implementation | Executing | Civil Supervisor | Structural Engineer | Week 6 | Medium | High | 6 | Wind load calc exceeded |  | Add ballast | Install tie‑downs | Open | Week 7 | Wind testing | Safety enforcement | https://docs.example.com/wind-uplift | Similar in 2020 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R087 | Improper sealing around mounts | Water leakage risk at rooftop wall mount | Construction | Environmental | Network Infrastructure | Civil Works Team | Data Center Link Integration | DCLI-005 | Implementation | Executing | Civil Supervisor | Contractor | Week 7 | Medium | High | 6 | Sealant gaps found |  | Apply proper sealant | Retest for leaks | Open | Week 8 | Leak testing | Environmental control | https://docs.example.com/mount-sealing | Leak case in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R088 | Improper grounding of racks | Grounding not compliant with electrical code | Electrical | Safety | Network Infrastructure | Electrical Works Team | Data Center Link Integration | DCLI-005 | Implementation | Executing | Electrical Supervisor | Contractor | Week 8 | High | High | 9 | Inspection found missing ground |  | Install proper grounding | Retest compliance | Open | Week 9 | Electrical inspection | Safety enforcement | https://docs.example.com/grounding-error | Grounding issue in 2022 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R089 | Power cable insulation failure | Insulation damaged during installation | Electrical | Quality | Network Infrastructure | Electrical Works Team | Data Center Link Integration | DCLI-005 | Implementation | Executing | Electrical Supervisor | Contractor | Week 8 | Medium | High | 6 | Visual inspection found damage |  | Replace cable | Retest insulation | Open | Week 9 | Cable testing | Quality enforcement | https://docs.example.com/cable-insulation | Failure in 2020 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R090 | Delay in electrical panel installation | Panels delivered late to site | Electrical | Logistics | Network Infrastructure | Electrical Works Team | Data Center Link Integration | DCLI-005 | Implementation | Executing | Electrical Supervisor | Vendor | Week 8 | Medium | Medium | 4 | Vendor shipment delayed |  | Reschedule installation | Use backup panels | Open | Week 9 | Delivery tracking | Logistics control | https://docs.example.com/panel-delay | Delay in 2021 | Primary | Medium | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R091 | Fiber splice loss above limit | High dB loss at splice points | Technical | Fiber | Network Infrastructure | Telecom Implementation Team | Data Center Link Integration | DCLI-005 | Implementation | Executing | Telecom Supervisor | Contractor | Week 9 | Medium | High | 6 | OTDR test shows high loss | Optical budget calc | Re-splice fibers | Replace connectors | Open | Week 10 | Optical testing | Performance tuning | https://docs.example.com/splice-loss | Similar in 2023 | Primary | High | Analysis – Quantitative |  | ✓ | ✓ |  |  | ✓
R092 | GSM antenna misalignment | Antenna not aligned to design azimuth | Technical | GSM | Network Infrastructure | Telecom Implementation Team | Data Center Link Integration | DCLI-005 | Implementation | Executing | Telecom Supervisor | Contractor | Week 9 | Medium | High | 6 | Alignment check failed |  | Realign antenna | Retest coverage | Open | Week 10 | Signal testing | Quality enforcement | https://docs.example.com/antenna-misalignment | Misalignment in 2020 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R093 | Integration software bug | Software error during site integration | Technical | Integration | Network Infrastructure | Telecom Implementation Team | Data Center Link Integration | DCLI-005 | Implementation | Executing | Telecom Supervisor | Vendor | Week 10 | Medium | High | 6 | Bug found in integration test |  | Apply patch | Retest integration | Open | Week 11 | Integration logs | Quality control | https://docs.example.com/integration-bug | Bug in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R094 | Failed acceptance test | Acceptance criteria not met during QA | Quality | Testing | Network Infrastructure | QA Team | Data Center Link Integration | DCLI-005 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | High | High | 9 | Test results below threshold |  | Identify root cause | Retest after fix | Open | Week 12 | Test logs | Quality enforcement | https://docs.example.com/acceptance-fail | Fail in 2022 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R095 | Missing as-built drawings | Final as-built documentation not prepared before acceptance | Quality | Documentation | Network Infrastructure | QA Team | Data Center Link Integration | DCLI-005 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | Medium | High | 6 | No updated drawings in repository |  | Prepare as-built set | Submit for approval | Open | Week 12 | Doc review | Documentation control | https://docs.example.com/missing-asbuilt | Similar gap in 2020 | Primary | High | Documentation | [5 empty] | ✓
R096 | Acceptance criteria misinterpretation | Stakeholders apply incorrect acceptance standards | Quality | Compliance | Network Infrastructure | QA Team | Data Center Link Integration | DCLI-005 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | Medium | High | 6 | Standards mismatch noted |  | Clarify acceptance checklist | Align with contract | Open | Week 12 | Acceptance review | Compliance enforcement | https://docs.example.com/criteria-error | Case in 2021 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R097 | Preventive maintenance schedule gap | Maintenance plan missing critical inspections | Maintenance | Planning | Network Infrastructure | Operations Team | Data Center Link Integration | DCLI-005 | Maintenance | Closing | Maintenance Lead | Stakeholders | Week 13 | Medium | Medium | 4 | Missing inspection tasks |  | Revise schedule | Train maintenance staff | Open | Week 14 | Plan review | Compliance check | https://docs.example.com/maintenance-gap | Gap in 2023 | Primary | Medium | Documentation | [5 empty] | ✓
R098 | Security breach risk | Unauthorized access to site during maintenance | Maintenance | Security | Network Infrastructure | Operations Team | Data Center Link Integration | DCLI-005 | Maintenance | Closing | Maintenance Lead | Security Contractor | Week 13 | High | High | 9 | Access control failure |  | Upgrade locks | Implement ID checks | Open | Week 14 | Security audit | Security enforcement | https://docs.example.com/security-breach | Breach in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R099 | Spare parts shortage | Insufficient spare parts for maintenance tasks | Maintenance | Logistics | Network Infrastructure | Operations Team | Data Center Link Integration | DCLI-005 | Maintenance | Closing | Maintenance Lead | Vendor | Week 13 | Medium | High | 6 | Inventory below threshold |  | Reorder parts | Use alternate supplier | Open | Week 14 | Inventory tracking | Logistics control | https://docs.example.com/spare-parts-shortage | Shortage in 2020 | Primary | High | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R100 | Preventive maintenance training gap | Maintenance staff not trained on new equipment | Maintenance | Training | Network Infrastructure | Operations Team | Data Center Link Integration | DCLI-005 | Maintenance | Closing | Maintenance Lead | Stakeholders | Week 13 | Medium | Medium | 4 | Training records incomplete |  | Conduct refresher training | Update manuals | Open | Week 14 | Training review | Compliance check | https://docs.example.com/training-gap | Gap in 2023 | Primary | Medium | Documentation | [5 empty] | ✓
R101 | Permit processing delay | Authority backlog slows Greenfield site approval | Requirements | Regulatory | Network Infrastructure | SAQ Team | Metro Fiber Expansion | NFX-004 | Requirements | Initiating | SAQ Lead | Municipal Authority | Week 1 | High | High | 9 | Permit queue extended |  | Follow up with authority | Adjust schedule | Open | Week 2 | Permit tracking | Regulatory enforcement | https://docs.example.com/permit-delay | Similar delay in 2021 | Primary | High | Risk Identification | ✓ |  |  |  |  | ✓
R102 | Boundary survey discrepancy | Survey data conflicts with municipal records | Requirements | Technical | Network Infrastructure | SAQ Team | Metro Fiber Expansion | NFX-004 | Requirements | Planning | SAQ Lead | Survey Contractor | Week 2 | Medium | High | 6 | Boundary mismatch found |  | Resurvey site | Update maps | Open | Week 3 | Survey review | Quality control | https://docs.example.com/survey-error | Error in 2020 | Primary | Medium | Analysis – Qualitative |  | ✓ |  |  |  | ✓
R103 | Community protest | Residents object to rooftop tower installation | Requirements | Stakeholder | Network Infrastructure | SAQ Team | Metro Fiber Expansion | NFX-004 | Requirements | Planning | SAQ Lead | Community Group | Week 3 | Medium | High | 6 | Objection raised in meeting |  | Engage community | Offer mitigation plan | Open | Week 4 | Stakeholder engagement | Conflict resolution | https://docs.example.com/community-opposition | Similar in 2022 | Primary | High | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R104 | Foundation settlement risk | Soil compaction inadequate for monopole base | Construction | Physical | Network Infrastructure | Civil Works Team | Metro Fiber Expansion | NFX-004 | Implementation | Executing | Civil Supervisor | Geotechnical Engineer | Week 5 | High | High | 9 | Settlement observed in test pit |  | Recompact soil | Reinforce foundation | Open | Week 6 | Foundation survey | Structural compliance | https://docs.example.com/foundation-settlement | Similar in 2020 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R105 | Incorrect tower plumb | Tower tilt exceeds tolerance during erection | Construction | Quality | Network Infrastructure | Civil Works Team | Metro Fiber Expansion | NFX-004 | Implementation | Executing | Civil Supervisor | Contractor | Week 6 | Medium | High | 6 | Plumb check failed |  | Realign tower | Retest alignment | Open | Week 7 | Alignment check | Quality enforcement | https://docs.example.com/tower-plumb-error | Error in 2023 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R106 | Rooftop wind uplift risk | Non‑penetrating pole at risk in high winds | Construction | Safety | Network Infrastructure | Civil Works Team | Metro Fiber Expansion | NFX-004 | Implementation | Executing | Civil Supervisor | Structural Engineer | Week 6 | Medium | High | 6 | Wind load calc exceeded |  | Add ballast | Install tie‑downs | Open | Week 7 | Wind testing | Safety enforcement | https://docs.example.com/wind-uplift | Similar in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R107 | Improper sealing around mounts | Water leakage risk at rooftop wall mount | Construction | Environmental | Network Infrastructure | Civil Works Team | Metro Fiber Expansion | NFX-004 | Implementation | Executing | Civil Supervisor | Contractor | Week 7 | Medium | High | 6 | Sealant gaps found |  | Apply proper sealant | Retest for leaks | Open | Week 8 | Leak testing | Environmental control | https://docs.example.com/mount-sealing | Leak case in 2020 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R108 | Improper grounding of racks | Grounding not compliant with electrical code | Electrical | Safety | Network Infrastructure | Electrical Works Team | Metro Fiber Expansion | NFX-004 | Implementation | Executing | Electrical Supervisor | Contractor | Week 8 | High | High | 9 | Inspection found missing ground |  | Install proper grounding | Retest compliance | Open | Week 9 | Electrical inspection | Safety enforcement | https://docs.example.com/grounding-error | Grounding issue in 2022 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R109 | Power cable insulation failure | Insulation damaged during installation | Electrical | Quality | Network Infrastructure | Electrical Works Team | Metro Fiber Expansion | NFX-004 | Implementation | Executing | Electrical Supervisor | Contractor | Week 8 | Medium | High | 6 | Visual inspection found damage |  | Replace cable | Retest insulation | Open | Week 9 | Cable testing | Quality enforcement | https://docs.example.com/cable-insulation | Failure in 2020 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R110 | Delay in electrical panel installation | Panels delivered late to site | Electrical | Logistics | Network Infrastructure | Electrical Works Team | Metro Fiber Expansion | NFX-004 | Implementation | Executing | Electrical Supervisor | Vendor | Week 8 | Medium | Medium | 4 | Vendor shipment delayed |  | Reschedule installation | Use backup panels | Open | Week 9 | Delivery tracking | Logistics control | https://docs.example.com/panel-delay | Delay in 2021 | Primary | Medium | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R111 | Fiber splice loss above limit | High dB loss at splice points | Technical | Fiber | Network Infrastructure | Telecom Implementation Team | Metro Fiber Expansion | NFX-004 | Implementation | Executing | Telecom Supervisor | Contractor | Week 9 | Medium | High | 6 | OTDR test shows high loss | Optical budget calc | Re-splice fibers | Replace connectors | Open | Week 10 | Optical testing | Performance tuning | https://docs.example.com/splice-loss | Similar in 2023 | Primary | High | Analysis – Quantitative |  | ✓ | ✓ |  |  | ✓
R112 | GSM antenna misalignment | Antenna not aligned to design azimuth | Technical | GSM | Network Infrastructure | Telecom Implementation Team | Metro Fiber Expansion | NFX-004 | Implementation | Executing | Telecom Supervisor | Contractor | Week 9 | Medium | High | 6 | Alignment check failed |  | Realign antenna | Retest coverage | Open | Week 10 | Signal testing | Quality enforcement | https://docs.example.com/antenna-misalignment | Misalignment in 2020 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R113 | Integration software bug | Software error during site integration | Technical | Integration | Network Infrastructure | Telecom Implementation Team | Metro Fiber Expansion | NFX-004 | Implementation | Executing | Telecom Supervisor | Vendor | Week 10 | Medium | High | 6 | Bug found in integration test |  | Apply patch | Retest integration | Open | Week 11 | Integration logs | Quality control | https://docs.example.com/integration-bug | Bug in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R114 | Failed acceptance test | Acceptance criteria not met during QA | Quality | Testing | Network Infrastructure | QA Team | Metro Fiber Expansion | NFX-004 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | High | High | 9 | Test results below threshold |  | Identify root cause | Retest after fix | Open | Week 12 | Test logs | Quality enforcement | https://docs.example.com/acceptance-fail | Fail in 2022 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R115 | Missing as-built drawings | Final as-built documentation not prepared before acceptance | Quality | Documentation | Network Infrastructure | QA Team | Metro Fiber Expansion | NFX-004 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | Medium | High | 6 | No updated drawings in repository |  | Prepare as-built set | Submit for approval | Open | Week 12 | Doc review | Documentation control | https://docs.example.com/missing-asbuilt | Similar gap in 2020 | Primary | High | Documentation | [5 empty] | ✓
R116 | Acceptance criteria misinterpretation | Stakeholders apply incorrect acceptance standards | Quality | Compliance | Network Infrastructure | QA Team | Metro Fiber Expansion | NFX-004 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | Medium | High | 6 | Standards mismatch noted |  | Clarify acceptance checklist | Align with contract | Open | Week 12 | Acceptance review | Compliance enforcement | https://docs.example.com/criteria-error | Case in 2021 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R117 | Preventive maintenance schedule gap | Maintenance plan missing critical inspections | Maintenance | Planning | Network Infrastructure | Operations Team | Metro Fiber Expansion | NFX-004 | Maintenance | Closing | Maintenance Lead | Stakeholders | Week 13 | Medium | Medium | 4 | Missing inspection tasks |  | Revise schedule | Train maintenance staff | Open | Week 14 | Plan review | Compliance check | https://docs.example.com/maintenance-gap | Gap in 2023 | Primary | Medium | Documentation | [5 empty] | ✓
R118 | Security breach risk | Unauthorized access to site during maintenance | Maintenance | Security | Network Infrastructure | Operations Team | Metro Fiber Expansion | NFX-004 | Maintenance | Closing | Maintenance Lead | Security Contractor | Week 13 | High | High | 9 | Access control failure |  | Upgrade locks | Implement ID checks | Open | Week 14 | Security audit | Security enforcement | https://docs.example.com/security-breach | Breach in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R119 | Spare parts shortage | Insufficient spare parts for maintenance tasks | Maintenance | Logistics | Network Infrastructure | Operations Team | Metro Fiber Expansion | NFX-004 | Maintenance | Closing | Maintenance Lead | Vendor | Week 13 | Medium | High | 6 | Inventory below threshold |  | Reorder parts | Use alternate supplier | Open | Week 14 | Inventory tracking | Logistics control | https://docs.example.com/spare-parts-shortage | Shortage in 2020 | Primary | High | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R120 | Preventive maintenance training gap | Maintenance staff not trained on new equipment | Maintenance | Training | Network Infrastructure | Operations Team | Metro Fiber Expansion | NFX-004 | Maintenance | Closing | Maintenance Lead | Stakeholders | Week 13 | Medium | Medium | 4 | Training records incomplete |  | Conduct refresher training | Update manuals | Open | Week 14 | Training review | Compliance check | https://docs.example.com/training-gap | Gap in 2023 | Primary | Medium | Documentation | [5 empty] | ✓
R121 | Permit approval delay | Municipal permit takes longer than expected | Requirements | Regulatory | Network Infrastructure | SAQ Team | Regional Backbone Upgrade | RBU-004 | Requirements | Initiating | SAQ Lead | Municipal Authority | Week 1 | High | High | 9 | Authority backlog noted |  | Follow up with authority | Adjust schedule | Open | Week 2 | Permit tracking | Regulatory enforcement | https://docs.example.com/permit-delay | Similar delay in 2023 | Primary | High | Risk Identification | ✓ |  |  |  |  | ✓
R122 | Landowner dispute | Landowner refuses rooftop site access | Requirements | Legal | Network Infrastructure | SAQ Team | Regional Backbone Upgrade | RBU-004 | Requirements | Initiating | SAQ Lead | Landowner | Week 1 | High | High | 9 | Dispute raised during negotiation |  | Engage legal team | Identify alternate site | Open | Week 2 | Stakeholder meeting | Legal enforcement | https://docs.example.com/land-dispute | Case in 2021 | Primary | High | Risk Identification | ✓ |  |  |  |  | ✓
R123 | Environmental clearance rejection | Environmental permit denied due to protected zone | Requirements | Environmental | Network Infrastructure | SAQ Team | Regional Backbone Upgrade | RBU-004 | Requirements | Planning | SAQ Lead | Environmental Authority | Week 2 | High | High | 9 | Protected area identified |  | Relocate site | Apply for exemption | Open | Week 3 | Permit tracking | Environmental compliance | https://docs.example.com/env-clearance | Similar in 2020 | Primary | High | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R124 | Foundation depth error | Monopole foundation depth below design spec | Construction | Quality | Network Infrastructure | Civil Works Team | Regional Backbone Upgrade | RBU-004 | Implementation | Executing | Civil Supervisor | Contractor | Week 5 | Medium | High | 6 | Inspection found shallow depth |  | Excavate deeper | Recast foundation | Open | Week 6 | Foundation survey | Quality enforcement | https://docs.example.com/foundation-error | Error in 2022 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R125 | Anchor bolt misalignment | Anchor bolts for self‑supporting tower misaligned | Construction | Quality | Network Infrastructure | Civil Works Team | Regional Backbone Upgrade | RBU-004 | Implementation | Executing | Civil Supervisor | Contractor | Week 6 | Medium | High | 6 | Template shift during casting |  | Realign bolts | Retest alignment | Open | Week 7 | Alignment check | Quality enforcement | https://docs.example.com/bolt-misalignment | Similar in 2021 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R126 | Rooftop wind uplift risk | Non‑penetrating pole at risk in high winds | Construction | Safety | Network Infrastructure | Civil Works Team | Regional Backbone Upgrade | RBU-004 | Implementation | Executing | Civil Supervisor | Structural Engineer | Week 6 | Medium | High | 6 | Wind load calc exceeded |  | Add ballast | Install tie‑downs | Open | Week 7 | Wind testing | Safety enforcement | https://docs.example.com/wind-uplift | Similar in 2020 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R127 | Improper sealing around mounts | Water leakage risk at rooftop wall mount | Construction | Environmental | Network Infrastructure | Civil Works Team | Regional Backbone Upgrade | RBU-004 | Implementation | Executing | Civil Supervisor | Contractor | Week 7 | Medium | High | 6 | Sealant gaps found |  | Apply proper sealant | Retest for leaks | Open | Week 8 | Leak testing | Environmental control | https://docs.example.com/mount-sealing | Leak case in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R128 | Improper grounding of racks | Grounding not compliant with electrical code | Electrical | Safety | Network Infrastructure | Electrical Works Team | Regional Backbone Upgrade | RBU-004 | Implementation | Executing | Electrical Supervisor | Contractor | Week 8 | High | High | 9 | Inspection found missing ground |  | Install proper grounding | Retest compliance | Open | Week 9 | Electrical inspection | Safety enforcement | https://docs.example.com/grounding-error | Grounding issue in 2023 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R129 | Power cable insulation failure | Insulation damaged during installation | Electrical | Quality | Network Infrastructure | Electrical Works Team | Regional Backbone Upgrade | RBU-004 | Implementation | Executing | Electrical Supervisor | Contractor | Week 8 | Medium | High | 6 | Visual inspection found damage |  | Replace cable | Retest insulation | Open | Week 9 | Cable testing | Quality enforcement | https://docs.example.com/cable-insulation | Failure in 2020 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R130 | Delay in electrical panel installation | Panels delivered late to site | Electrical | Logistics | Network Infrastructure | Electrical Works Team | Regional Backbone Upgrade | RBU-004 | Implementation | Executing | Electrical Supervisor | Vendor | Week 8 | Medium | Medium | 4 | Vendor shipment delayed |  | Reschedule installation | Use backup panels | Open | Week 9 | Delivery tracking | Logistics control | https://docs.example.com/panel-delay | Delay in 2021 | Primary | Medium | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R131 | Fiber splice loss above limit | High dB loss at splice points | Technical | Fiber | Network Infrastructure | Telecom Implementation Team | Regional Backbone Upgrade | RBU-004 | Implementation | Executing | Telecom Supervisor | Contractor | Week 9 | Medium | High | 6 | OTDR test shows high loss | Optical budget calc | Re-splice fibers | Replace connectors | Open | Week 10 | Optical testing | Performance tuning | https://docs.example.com/splice-loss | Similar in 2022 | Primary | High | Analysis – Quantitative |  | ✓ | ✓ |  |  | ✓
R132 | GSM antenna misalignment | Antenna not aligned to design azimuth | Technical | GSM | Network Infrastructure | Telecom Implementation Team | Regional Backbone Upgrade | RBU-004 | Implementation | Executing | Telecom Supervisor | Contractor | Week 9 | Medium | High | 6 | Alignment check failed |  | Realign antenna | Retest coverage | Open | Week 10 | Signal testing | Quality enforcement | https://docs.example.com/antenna-misalignment | Misalignment in 2020 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R133 | Integration software bug | Software error during site integration | Technical | Integration | Network Infrastructure | Telecom Implementation Team | Regional Backbone Upgrade | RBU-004 | Implementation | Executing | Telecom Supervisor | Vendor | Week 10 | Medium | High | 6 | Bug found in integration test |  | Apply patch | Retest integration | Open | Week 11 | Integration logs | Quality control | https://docs.example.com/integration-bug | Bug in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R134 | Failed acceptance test | Acceptance criteria not met during QA | Quality | Testing | Network Infrastructure | QA Team | Regional Backbone Upgrade | RBU-004 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | High | High | 9 | Test results below threshold |  | Identify root cause | Retest after fix | Open | Week 12 | Test logs | Quality enforcement | https://docs.example.com/acceptance-fail | Fail in 2023 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R135 | Missing as-built drawings | Final as-built documentation not prepared before acceptance | Quality | Documentation | Network Infrastructure | QA Team | Regional Backbone Upgrade | RBU-004 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | Medium | High | 6 | No updated drawings in repository |  | Prepare as-built set | Submit for approval | Open | Week 12 | Doc review | Documentation control | https://docs.example.com/missing-asbuilt | Similar gap in 2021 | Primary | High | Documentation | [5 empty] | ✓
R136 | Acceptance criteria misinterpretation | Stakeholders apply incorrect acceptance standards | Quality | Compliance | Network Infrastructure | QA Team | Regional Backbone Upgrade | RBU-004 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | Medium | High | 6 | Standards mismatch noted |  | Clarify acceptance checklist | Align with contract | Open | Week 12 | Acceptance review | Compliance enforcement | https://docs.example.com/criteria-error | Case in 2020 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R137 | Preventive maintenance schedule gap | Maintenance plan missing critical inspections | Maintenance | Planning | Network Infrastructure | Operations Team | Regional Backbone Upgrade | RBU-004 | Maintenance | Closing | Maintenance Lead | Stakeholders | Week 13 | Medium | Medium | 4 | Missing inspection tasks |  | Revise schedule | Train maintenance staff | Open | Week 14 | Plan review | Compliance check | https://docs.example.com/maintenance-gap | Gap in 2022 | Primary | Medium | Documentation | [5 empty] | ✓
R138 | Security breach risk | Unauthorized access to site during maintenance | Maintenance | Security | Network Infrastructure | Operations Team | Regional Backbone Upgrade | RBU-004 | Maintenance | Closing | Maintenance Lead | Security Contractor | Week 13 | High | High | 9 | Access control failure |  | Upgrade locks | Implement ID checks | Open | Week 14 | Security audit | Security enforcement | https://docs.example.com/security-breach | Breach in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R139 | Spare parts shortage | Insufficient spare parts for maintenance tasks | Maintenance | Logistics | Network Infrastructure | Operations Team | Regional Backbone Upgrade | RBU-004 | Maintenance | Closing | Maintenance Lead | Vendor | Week 13 | Medium | High | 6 | Inventory below threshold |  | Reorder parts | Use alternate supplier | Open | Week 14 | Inventory tracking | Logistics control | https://docs.example.com/spare-parts-shortage | Shortage in 2020 | Primary | High | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R140 | Preventive maintenance training gap | Maintenance staff not trained on new equipment | Maintenance | Training | Network Infrastructure | Operations Team | Regional Backbone Upgrade | RBU-004 | Maintenance | Closing | Maintenance Lead | Stakeholders | Week 13 | Medium | Medium | 4 | Training records incomplete |  | Conduct refresher training | Update manuals | Open | Week 14 | Training review | Compliance check | https://docs.example.com/training-gap | Gap in 2023 | Primary | Medium | Documentation | [5 empty] | ✓
R141 | Permit processing delay | Authority backlog slows rooftop site approval | Requirements | Regulatory | Network Infrastructure | SAQ Team | Industrial Zone Connectivity | IZC-005 | Requirements | Initiating | SAQ Lead | Municipal Authority | Week 1 | High | High | 9 | Permit queue extended |  | Follow up with authority | Adjust schedule | Open | Week 2 | Permit tracking | Regulatory enforcement | https://docs.example.com/permit-delay | Similar delay in 2022 | Primary | High | Risk Identification | ✓ |  |  |  |  | ✓
R142 | Boundary survey discrepancy | Survey data conflicts with municipal records | Requirements | Technical | Network Infrastructure | SAQ Team | Industrial Zone Connectivity | IZC-005 | Requirements | Planning | SAQ Lead | Survey Contractor | Week 2 | Medium | High | 6 | Boundary mismatch found |  | Resurvey site | Update maps | Open | Week 3 | Survey review | Quality control | https://docs.example.com/survey-error | Error in 2020 | Primary | Medium | Analysis – Qualitative |  | ✓ |  |  |  | ✓
R143 | Community protest | Residents object to Greenfield tower construction | Requirements | Stakeholder | Network Infrastructure | SAQ Team | Industrial Zone Connectivity | IZC-005 | Requirements | Planning | SAQ Lead | Community Group | Week 3 | Medium | High | 6 | Objection raised in meeting |  | Engage community | Offer mitigation plan | Open | Week 4 | Stakeholder engagement | Conflict resolution | https://docs.example.com/community-opposition | Similar in 2021 | Primary | High | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R144 | Foundation settlement risk | Soil compaction inadequate for monopole base | Construction | Physical | Network Infrastructure | Civil Works Team | Industrial Zone Connectivity | IZC-005 | Implementation | Executing | Civil Supervisor | Geotechnical Engineer | Week 5 | High | High | 9 | Settlement observed in test pit |  | Recompact soil | Reinforce foundation | Open | Week 6 | Foundation survey | Structural compliance | https://docs.example.com/foundation-settlement | Similar in 2020 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R145 | Incorrect tower plumb | Tower tilt exceeds tolerance during erection | Construction | Quality | Network Infrastructure | Civil Works Team | Industrial Zone Connectivity | IZC-005 | Implementation | Executing | Civil Supervisor | Contractor | Week 6 | Medium | High | 6 | Plumb check failed |  | Realign tower | Retest alignment | Open | Week 7 | Alignment check | Quality enforcement | https://docs.example.com/tower-plumb-error | Error in 2023 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R146 | Rooftop wind uplift risk | Non‑penetrating pole at risk in high winds | Construction | Safety | Network Infrastructure | Civil Works Team | Industrial Zone Connectivity | IZC-005 | Implementation | Executing | Civil Supervisor | Structural Engineer | Week 6 | Medium | High | 6 | Wind load calc exceeded |  | Add ballast | Install tie‑downs | Open | Week 7 | Wind testing | Safety enforcement | https://docs.example.com/wind-uplift | Similar in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R147 | Improper sealing around mounts | Water leakage risk at rooftop wall mount | Construction | Environmental | Network Infrastructure | Civil Works Team | Industrial Zone Connectivity | IZC-005 | Implementation | Executing | Civil Supervisor | Contractor | Week 7 | Medium | High | 6 | Sealant gaps found |  | Apply proper sealant | Retest for leaks | Open | Week 8 | Leak testing | Environmental control | https://docs.example.com/mount-sealing | Leak case in 2020 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R148 | Improper grounding of racks | Grounding not compliant with electrical code | Electrical | Safety | Network Infrastructure | Electrical Works Team | Industrial Zone Connectivity | IZC-005 | Implementation | Executing | Electrical Supervisor | Contractor | Week 8 | High | High | 9 | Inspection found missing ground |  | Install proper grounding | Retest compliance | Open | Week 9 | Electrical inspection | Safety enforcement | https://docs.example.com/grounding-error | Grounding issue in 2022 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R149 | Power cable insulation failure | Insulation damaged during installation | Electrical | Quality | Network Infrastructure | Electrical Works Team | Industrial Zone Connectivity | IZC-005 | Implementation | Executing | Electrical Supervisor | Contractor | Week 8 | Medium | High | 6 | Visual inspection found damage |  | Replace cable | Retest insulation | Open | Week 9 | Cable testing | Quality enforcement | https://docs.example.com/cable-insulation | Failure in 2020 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R150 | Delay in electrical panel installation | Panels delivered late to site | Electrical | Logistics | Network Infrastructure | Electrical Works Team | Industrial Zone Connectivity | IZC-005 | Implementation | Executing | Electrical Supervisor | Vendor | Week 8 | Medium | Medium | 4 | Vendor shipment delayed |  | Reschedule installation | Use backup panels | Open | Week 9 | Delivery tracking | Logistics control | https://docs.example.com/panel-delay | Delay in 2021 | Primary | Medium | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R151 | Fiber splice loss above limit | High dB loss at splice points | Technical | Fiber | Network Infrastructure | Telecom Implementation Team | Industrial Zone Connectivity | IZC-005 | Implementation | Executing | Telecom Supervisor | Contractor | Week 9 | Medium | High | 6 | OTDR test shows high loss | Optical budget calc | Re-splice fibers | Replace connectors | Open | Week 10 | Optical testing | Performance tuning | https://docs.example.com/splice-loss | Similar in 2023 | Primary | High | Analysis – Quantitative |  | ✓ | ✓ |  |  | ✓
R152 | GSM antenna misalignment | Antenna not aligned to design azimuth | Technical | GSM | Network Infrastructure | Telecom Implementation Team | Industrial Zone Connectivity | IZC-005 | Implementation | Executing | Telecom Supervisor | Contractor | Week 9 | Medium | High | 6 | Alignment check failed |  | Realign antenna | Retest coverage | Open | Week 10 | Signal testing | Quality enforcement | https://docs.example.com/antenna-misalignment | Misalignment in 2020 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R153 | Integration software bug | Software error during site integration | Technical | Integration | Network Infrastructure | Telecom Implementation Team | Industrial Zone Connectivity | IZC-005 | Implementation | Executing | Telecom Supervisor | Vendor | Week 10 | Medium | High | 6 | Bug found in integration test |  | Apply patch | Retest integration | Open | Week 11 | Integration logs | Quality control | https://docs.example.com/integration-bug | Bug in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R154 | Failed acceptance test | Acceptance criteria not met during QA | Quality | Testing | Network Infrastructure | QA Team | Industrial Zone Connectivity | IZC-005 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | High | High | 9 | Test results below threshold |  | Identify root cause | Retest after fix | Open | Week 12 | Test logs | Quality enforcement | https://docs.example.com/acceptance-fail | Fail in 2022 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R155 | Missing as-built drawings | Final as-built documentation not prepared before acceptance | Quality | Documentation | Network Infrastructure | QA Team | Industrial Zone Connectivity | IZC-005 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | Medium | High | 6 | No updated drawings in repository |  | Prepare as-built set | Submit for approval | Open | Week 12 | Doc review | Documentation control | https://docs.example.com/missing-asbuilt | Similar gap in 2020 | Primary | High | Documentation | [5 empty] | ✓
R156 | Acceptance criteria misinterpretation | Stakeholders apply incorrect acceptance standards | Quality | Compliance | Network Infrastructure | QA Team | Industrial Zone Connectivity | IZC-005 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | Medium | High | 6 | Standards mismatch noted |  | Clarify acceptance checklist | Align with contract | Open | Week 12 | Acceptance review | Compliance enforcement | https://docs.example.com/criteria-error | Case in 2021 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R157 | Preventive maintenance schedule gap | Maintenance plan missing critical inspections | Maintenance | Planning | Network Infrastructure | Operations Team | Industrial Zone Connectivity | IZC-005 | Maintenance | Closing | Maintenance Lead | Stakeholders | Week 13 | Medium | Medium | 4 | Missing inspection tasks |  | Revise schedule | Train maintenance staff | Open | Week 14 | Plan review | Compliance check | https://docs.example.com/maintenance-gap | Gap in 2023 | Primary | Medium | Documentation | [5 empty] | ✓
R158 | Security breach risk | Unauthorized access to site during maintenance | Maintenance | Security | Network Infrastructure | Operations Team | Industrial Zone Connectivity | IZC-005 | Maintenance | Closing | Maintenance Lead | Security Contractor | Week 13 | High | High | 9 | Access control failure |  | Upgrade locks | Implement ID checks | Open | Week 14 | Security audit | Security enforcement | https://docs.example.com/security-breach | Breach in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R159 | Spare parts shortage | Insufficient spare parts for maintenance tasks | Maintenance | Logistics | Network Infrastructure | Operations Team | Industrial Zone Connectivity | IZC-005 | Maintenance | Closing | Maintenance Lead | Vendor | Week 13 | Medium | High | 6 | Inventory below threshold |  | Reorder parts | Use alternate supplier | Open | Week 14 | Inventory tracking | Logistics control | https://docs.example.com/spare-parts-shortage | Shortage in 2020 | Primary | High | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R160 | Preventive maintenance training gap | Maintenance staff not trained on new equipment | Maintenance | Training | Network Infrastructure | Operations Team | Industrial Zone Connectivity | IZC-005 | Maintenance | Closing | Maintenance Lead | Stakeholders | Week 13 | Medium | Medium | 4 | Training records incomplete |  | Conduct refresher training | Update manuals | Open | Week 14 | Training review | Compliance check | https://docs.example.com/training-gap | Gap in 2023 | Primary | Medium | Documentation | [5 empty] | ✓
R161 | Permit approval delay | Municipal permit takes longer than expected | Requirements | Regulatory | Network Infrastructure | SAQ Team | Smart City Node Deployment | SCN-006 | Requirements | Initiating | SAQ Lead | Municipal Authority | Week 1 | High | High | 9 | Authority backlog noted |  | Follow up with authority | Adjust schedule | Open | Week 2 | Permit tracking | Regulatory enforcement | https://docs.example.com/permit-delay | Similar delay in 2022 | Primary | High | Risk Identification | ✓ |  |  |  |  | ✓
R162 | Landowner dispute | Landowner refuses rooftop site access | Requirements | Legal | Network Infrastructure | SAQ Team | Smart City Node Deployment | SCN-006 | Requirements | Initiating | SAQ Lead | Landowner | Week 1 | High | High | 9 | Dispute raised during negotiation |  | Engage legal team | Identify alternate site | Open | Week 2 | Stakeholder meeting | Legal enforcement | https://docs.example.com/land-dispute | Case in 2021 | Primary | High | Risk Identification | ✓ |  |  |  |  | ✓
R163 | Environmental clearance rejection | Environmental permit denied due to protected zone | Requirements | Environmental | Network Infrastructure | SAQ Team | Smart City Node Deployment | SCN-006 | Requirements | Planning | SAQ Lead | Environmental Authority | Week 2 | High | High | 9 | Protected area identified |  | Relocate site | Apply for exemption | Open | Week 3 | Permit tracking | Environmental compliance | https://docs.example.com/env-clearance | Similar in 2020 | Primary | High | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R164 | Foundation depth error | Monopole foundation depth below design spec | Construction | Quality | Network Infrastructure | Civil Works Team | Smart City Node Deployment | SCN-006 | Implementation | Executing | Civil Supervisor | Contractor | Week 5 | Medium | High | 6 | Inspection found shallow depth |  | Excavate deeper | Recast foundation | Open | Week 6 | Foundation survey | Quality enforcement | https://docs.example.com/foundation-error | Error in 2023 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R165 | Anchor bolt misalignment | Anchor bolts for self‑supporting tower misaligned | Construction | Quality | Network Infrastructure | Civil Works Team | Smart City Node Deployment | SCN-006 | Implementation | Executing | Civil Supervisor | Contractor | Week 6 | Medium | High | 6 | Template shift during casting |  | Realign bolts | Retest alignment | Open | Week 7 | Alignment check | Quality enforcement | https://docs.example.com/bolt-misalignment | Similar in 2021 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R166 | Rooftop wind uplift risk | Non‑penetrating pole at risk in high winds | Construction | Safety | Network Infrastructure | Civil Works Team | Smart City Node Deployment | SCN-006 | Implementation | Executing | Civil Supervisor | Structural Engineer | Week 6 | Medium | High | 6 | Wind load calc exceeded |  | Add ballast | Install tie‑downs | Open | Week 7 | Wind testing | Safety enforcement | https://docs.example.com/wind-uplift | Similar in 2020 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R167 | Improper sealing around mounts | Water leakage risk at rooftop wall mount | Construction | Environmental | Network Infrastructure | Civil Works Team | Smart City Node Deployment | SCN-006 | Implementation | Executing | Civil Supervisor | Contractor | Week 7 | Medium | High | 6 | Sealant gaps found |  | Apply proper sealant | Retest for leaks | Open | Week 8 | Leak testing | Environmental control | https://docs.example.com/mount-sealing | Leak case in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R168 | Improper grounding of racks | Grounding not compliant with electrical code | Electrical | Safety | Network Infrastructure | Electrical Works Team | Smart City Node Deployment | SCN-006 | Implementation | Executing | Electrical Supervisor | Contractor | Week 8 | High | High | 9 | Inspection found missing ground |  | Install proper grounding | Retest compliance | Open | Week 9 | Electrical inspection | Safety enforcement | https://docs.example.com/grounding-error | Grounding issue in 2022 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R169 | Power cable insulation failure | Insulation damaged during installation | Electrical | Quality | Network Infrastructure | Electrical Works Team | Smart City Node Deployment | SCN-006 | Implementation | Executing | Electrical Supervisor | Contractor | Week 8 | Medium | High | 6 | Visual inspection found damage |  | Replace cable | Retest insulation | Open | Week 9 | Cable testing | Quality enforcement | https://docs.example.com/cable-insulation | Failure in 2020 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R170 | Delay in electrical panel installation | Panels delivered late to site | Electrical | Logistics | Network Infrastructure | Electrical Works Team | Smart City Node Deployment | SCN-006 | Implementation | Executing | Electrical Supervisor | Vendor | Week 8 | Medium | Medium | 4 | Vendor shipment delayed |  | Reschedule installation | Use backup panels | Open | Week 9 | Delivery tracking | Logistics control | https://docs.example.com/panel-delay | Delay in 2021 | Primary | Medium | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R171 | Fiber splice loss above limit | High dB loss at splice points | Technical | Fiber | Network Infrastructure | Telecom Implementation Team | Smart City Node Deployment | SCN-006 | Implementation | Executing | Telecom Supervisor | Contractor | Week 9 | Medium | High | 6 | OTDR test shows high loss | Optical budget calc | Re-splice fibers | Replace connectors | Open | Week 10 | Optical testing | Performance tuning | https://docs.example.com/splice-loss | Similar in 2023 | Primary | High | Analysis – Quantitative |  | ✓ | ✓ |  |  | ✓
R172 | GSM antenna misalignment | Antenna not aligned to design azimuth | Technical | GSM | Network Infrastructure | Telecom Implementation Team | Smart City Node Deployment | SCN-006 | Implementation | Executing | Telecom Supervisor | Contractor | Week 9 | Medium | High | 6 | Alignment check failed |  | Realign antenna | Retest coverage | Open | Week 10 | Signal testing | Quality enforcement | https://docs.example.com/antenna-misalignment | Misalignment in 2020 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R173 | Integration software bug | Software error during site integration | Technical | Integration | Network Infrastructure | Telecom Implementation Team | Smart City Node Deployment | SCN-006 | Implementation | Executing | Telecom Supervisor | Vendor | Week 10 | Medium | High | 6 | Bug found in integration test |  | Apply patch | Retest integration | Open | Week 11 | Integration logs | Quality control | https://docs.example.com/integration-bug | Bug in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R174 | Failed acceptance test | Acceptance criteria not met during QA | Quality | Testing | Network Infrastructure | QA Team | Smart City Node Deployment | SCN-006 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | High | High | 9 | Test results below threshold |  | Identify root cause | Retest after fix | Open | Week 12 | Test logs | Quality enforcement | https://docs.example.com/acceptance-fail | Fail in 2022 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R175 | Missing as-built drawings | Final as-built documentation not prepared before acceptance | Quality | Documentation | Network Infrastructure | QA Team | Smart City Node Deployment | SCN-006 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | Medium | High | 6 | No updated drawings in repository |  | Prepare as-built set | Submit for approval | Open | Week 12 | Doc review | Documentation control | https://docs.example.com/missing-asbuilt | Similar gap in 2020 | Primary | High | Documentation | [5 empty] | ✓
R176 | Acceptance criteria misinterpretation | Stakeholders apply incorrect acceptance standards | Quality | Compliance | Network Infrastructure | QA Team | Smart City Node Deployment | SCN-006 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | Medium | High | 6 | Standards mismatch noted |  | Clarify acceptance checklist | Align with contract | Open | Week 12 | Acceptance review | Compliance enforcement | https://docs.example.com/criteria-error | Case in 2021 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R177 | Preventive maintenance schedule gap | Maintenance plan missing critical inspections | Maintenance | Planning | Network Infrastructure | Operations Team | Smart City Node Deployment | SCN-006 | Maintenance | Closing | Maintenance Lead | Stakeholders | Week 13 | Medium | Medium | 4 | Missing inspection tasks |  | Revise schedule | Train maintenance staff | Open | Week 14 | Plan review | Compliance check | https://docs.example.com/maintenance-gap | Gap in 2023 | Primary | Medium | Documentation | [5 empty] | ✓
R178 | Security breach risk | Unauthorized access to site during maintenance | Maintenance | Security | Network Infrastructure | Operations Team | Smart City Node Deployment | SCN-006 | Maintenance | Closing | Maintenance Lead | Security Contractor | Week 13 | High | High | 9 | Access control failure |  | Upgrade locks | Implement ID checks | Open | Week 14 | Security audit | Security enforcement | https://docs.example.com/security-breach | Breach in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R179 | Spare parts shortage | Insufficient spare parts for maintenance tasks | Maintenance | Logistics | Network Infrastructure | Operations Team | Smart City Node Deployment | SCN-006 | Maintenance | Closing | Maintenance Lead | Vendor | Week 13 | Medium | High | 6 | Inventory below threshold |  | Reorder parts | Use alternate supplier | Open | Week 14 | Inventory tracking | Logistics control | https://docs.example.com/spare-parts-shortage | Shortage in 2020 | Primary | High | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R180 | Preventive maintenance training gap | Maintenance staff not trained on new equipment | Maintenance | Training | Network Infrastructure | Operations Team | Smart City Node Deployment | SCN-006 | Maintenance | Closing | Maintenance Lead | Stakeholders | Week 13 | Medium | Medium | 4 | Training records incomplete |  | Conduct refresher training | Update manuals | Open | Week 14 | Training review | Compliance check | https://docs.example.com/training-gap | Gap in 2023 | Primary | Medium | Documentation | [5 empty] | ✓
R181 | Permit processing delay | Authority backlog slows Greenfield site approval | Requirements | Regulatory | Network Infrastructure | SAQ Team | Regional IoT Hub Deployment | RIHD-007 | Requirements | Initiating | SAQ Lead | Municipal Authority | Week 1 | High | High | 9 | Permit queue extended |  | Follow up with authority | Adjust schedule | Open | Week 2 | Permit tracking | Regulatory enforcement | https://docs.example.com/permit-delay | Similar delay in 2021 | Primary | High | Risk Identification | ✓ |  |  |  |  | ✓
R182 | Boundary survey discrepancy | Survey data conflicts with municipal records | Requirements | Technical | Network Infrastructure | SAQ Team | Regional IoT Hub Deployment | RIHD-007 | Requirements | Planning | SAQ Lead | Survey Contractor | Week 2 | Medium | High | 6 | Boundary mismatch found |  | Resurvey site | Update maps | Open | Week 3 | Survey review | Quality control | https://docs.example.com/survey-error | Error in 2020 | Primary | Medium | Analysis – Qualitative |  | ✓ |  |  |  | ✓
R183 | Community protest | Residents object to rooftop tower installation | Requirements | Stakeholder | Network Infrastructure | SAQ Team | Regional IoT Hub Deployment | RIHD-007 | Requirements | Planning | SAQ Lead | Community Group | Week 3 | Medium | High | 6 | Objection raised in meeting |  | Engage community | Offer mitigation plan | Open | Week 4 | Stakeholder engagement | Conflict resolution | https://docs.example.com/community-opposition | Similar in 2022 | Primary | High | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R184 | Foundation settlement risk | Soil compaction inadequate for monopole base | Construction | Physical | Network Infrastructure | Civil Works Team | Regional IoT Hub Deployment | RIHD-007 | Implementation | Executing | Civil Supervisor | Geotechnical Engineer | Week 5 | High | High | 9 | Settlement observed in test pit |  | Recompact soil | Reinforce foundation | Open | Week 6 | Foundation survey | Structural compliance | https://docs.example.com/foundation-settlement | Similar in 2020 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R185 | Incorrect tower plumb | Tower tilt exceeds tolerance during erection | Construction | Quality | Network Infrastructure | Civil Works Team | Regional IoT Hub Deployment | RIHD-007 | Implementation | Executing | Civil Supervisor | Contractor | Week 6 | Medium | High | 6 | Plumb check failed |  | Realign tower | Retest alignment | Open | Week 7 | Alignment check | Quality enforcement | https://docs.example.com/tower-plumb-error | Error in 2023 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R186 | Rooftop wind uplift risk | Non‑penetrating pole at risk in high winds | Construction | Safety | Network Infrastructure | Civil Works Team | Regional IoT Hub Deployment | RIHD-007 | Implementation | Executing | Civil Supervisor | Structural Engineer | Week 6 | Medium | High | 6 | Wind load calc exceeded |  | Add ballast | Install tie‑downs | Open | Week 7 | Wind testing | Safety enforcement | https://docs.example.com/wind-uplift | Similar in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R187 | Improper sealing around mounts | Water leakage risk at rooftop wall mount | Construction | Environmental | Network Infrastructure | Civil Works Team | Regional IoT Hub Deployment | RIHD-007 | Implementation | Executing | Civil Supervisor | Contractor | Week 7 | Medium | High | 6 | Sealant gaps found |  | Apply proper sealant | Retest for leaks | Open | Week 8 | Leak testing | Environmental control | https://docs.example.com/mount-sealing | Leak case in 2020 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R188 | Improper grounding of racks | Grounding not compliant with electrical code | Electrical | Safety | Network Infrastructure | Electrical Works Team | Regional IoT Hub Deployment | RIHD-007 | Implementation | Executing | Electrical Supervisor | Contractor | Week 8 | High | High | 9 | Inspection found missing ground |  | Install proper grounding | Retest compliance | Open | Week 9 | Electrical inspection | Safety enforcement | https://docs.example.com/grounding-error | Grounding issue in 2022 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R189 | Power cable insulation failure | Insulation damaged during installation | Electrical | Quality | Network Infrastructure | Electrical Works Team | Regional IoT Hub Deployment | RIHD-007 | Implementation | Executing | Electrical Supervisor | Contractor | Week 8 | Medium | High | 6 | Visual inspection found damage |  | Replace cable | Retest insulation | Open | Week 9 | Cable testing | Quality enforcement | https://docs.example.com/cable-insulation | Failure in 2020 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R190 | Delay in electrical panel installation | Panels delivered late to site | Electrical | Logistics | Network Infrastructure | Electrical Works Team | Regional IoT Hub Deployment | RIHD-007 | Implementation | Executing | Electrical Supervisor | Vendor | Week 8 | Medium | Medium | 4 | Vendor shipment delayed |  | Reschedule installation | Use backup panels | Open | Week 9 | Delivery tracking | Logistics control | https://docs.example.com/panel-delay | Delay in 2021 | Primary | Medium | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R191 | Fiber splice loss above limit | High dB loss at splice points | Technical | Fiber | Network Infrastructure | Telecom Implementation Team | Regional IoT Hub Deployment | RIHD-007 | Implementation | Executing | Telecom Supervisor | Contractor | Week 9 | Medium | High | 6 | OTDR test shows high loss | Optical budget calc | Re-splice fibers | Replace connectors | Open | Week 10 | Optical testing | Performance tuning | https://docs.example.com/splice-loss | Similar in 2023 | Primary | High | Analysis – Quantitative |  | ✓ | ✓ |  |  | ✓
R192 | GSM antenna misalignment | Antenna not aligned to design azimuth | Technical | GSM | Network Infrastructure | Telecom Implementation Team | Regional IoT Hub Deployment | RIHD-007 | Implementation | Executing | Telecom Supervisor | Contractor | Week 9 | Medium | High | 6 | Alignment check failed |  | Realign antenna | Retest coverage | Open | Week 10 | Signal testing | Quality enforcement | https://docs.example.com/antenna-misalignment | Misalignment in 2020 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R193 | Integration software bug | Software error during site integration | Technical | Integration | Network Infrastructure | Telecom Implementation Team | Regional IoT Hub Deployment | RIHD-007 | Implementation | Executing | Telecom Supervisor | Vendor | Week 10 | Medium | High | 6 | Bug found in integration test |  | Apply patch | Retest integration | Open | Week 11 | Integration logs | Quality control | https://docs.example.com/integration-bug | Bug in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R194 | Failed acceptance test | Acceptance criteria not met during QA | Quality | Testing | Network Infrastructure | QA Team | Regional IoT Hub Deployment | RIHD-007 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | High | High | 9 | Test results below threshold |  | Identify root cause | Retest after fix | Open | Week 12 | Test logs | Quality enforcement | https://docs.example.com/acceptance-fail | Fail in 2022 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R195 | Missing as-built drawings | Final as-built documentation not prepared before acceptance | Quality | Documentation | Network Infrastructure | QA Team | Regional IoT Hub Deployment | RIHD-007 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | Medium | High | 6 | No updated drawings in repository |  | Prepare as-built set | Submit for approval | Open | Week 12 | Doc review | Documentation control | https://docs.example.com/missing-asbuilt | Similar gap in 2020 | Primary | High | Documentation | [5 empty] | ✓
R196 | Acceptance criteria misinterpretation | Stakeholders apply incorrect acceptance standards | Quality | Compliance | Network Infrastructure | QA Team | Regional IoT Hub Deployment | RIHD-007 | Testing | Monitoring & Controlling | QA Lead | Stakeholders | Week 11 | Medium | High | 6 | Standards mismatch noted |  | Clarify acceptance checklist | Align with contract | Open | Week 12 | Acceptance review | Compliance enforcement | https://docs.example.com/criteria-error | Case in 2021 | Primary | High | Controlling |  |  |  | ✓ | ✓ | ✓ | ✓
R197 | Preventive maintenance schedule gap | Maintenance plan missing critical inspections | Maintenance | Planning | Network Infrastructure | Operations Team | Regional IoT Hub Deployment | RIHD-007 | Maintenance | Closing | Maintenance Lead | Stakeholders | Week 13 | Medium | Medium | 4 | Missing inspection tasks |  | Revise schedule | Train maintenance staff | Open | Week 14 | Plan review | Compliance check | https://docs.example.com/maintenance-gap | Gap in 2023 | Primary | Medium | Documentation | [5 empty] | ✓
R198 | Security breach risk | Unauthorized access to site during maintenance | Maintenance | Security | Network Infrastructure | Operations Team | Regional IoT Hub Deployment | RIHD-007 | Maintenance | Closing | Maintenance Lead | Security Contractor | Week 13 | High | High | 9 | Access control failure |  | Upgrade locks | Implement ID checks | Open | Week 14 | Security audit | Security enforcement | https://docs.example.com/security-breach | Breach in 2021 | Primary | High | Monitoring |  |  |  | ✓ | ✓ |  | ✓
R199 | Spare parts shortage | Insufficient spare parts for maintenance tasks | Maintenance | Logistics | Network Infrastructure | Operations Team | Regional IoT Hub Deployment | RIHD-007 | Maintenance | Closing | Maintenance Lead | Vendor | Week 13 | Medium | High | 6 | Inventory below threshold |  | Reorder parts | Use alternate supplier | Open | Week 14 | Inventory tracking | Logistics control | https://docs.example.com/spare-parts-shortage | Shortage in 2020 | Primary | High | Response Planning |  | ✓ | ✓ | ✓ |  | ✓
R200 | Preventive maintenance training gap | Maintenance staff not trained on new equipment | Maintenance | Training | Network Infrastructure | Operations Team | Regional IoT Hub Deployment | RIHD-007 | Maintenance | Closing | Maintenance Lead | Stakeholders | Week 13 | Medium | Medium | 4 | Training records incomplete |  | Conduct refresher training | Update manuals | Open | Week 14 | Training review | Compliance check | https://docs.example.com/training-gap | Gap in 2023 | Primary | Medium | Documentation | [5 empty] | ✓